## Sheet1
VR Journalism Project
✓ | Task | Description | Name | Due Date
| Video Player | Just getting a video up and running. making sure the video is displayed right. | Brandon B | Tuesday 12 | Requirements | In Progress | Testing | Merging | Done
| UI Controls | A UI Manager, which is a singleton mediator that has delegation that other classes can bind/subscribe to. Additionally, to design it. | Juriel G | Tuesday 12
| Video Switching | Allowing Videos to be switch using the a list of videos and switching one by one when they are done. However it must loop back when at the last video. | Juriel G | Friday 15
| Play Audio | Find and play some scenic Audio Clips that aide in telling a story. Audioclips must be Creative Commons 0 (Public Domain), or Attribution (Name of sound and author recorded) and play audio clips randomly. | Nicholas M | Tuesday 12
| Subtitles | We need some subtitles and a way to deliver the message to the screen. When the video/audio has triggered. And must fade away. | Brandon B | Friday 15
| 3D Models | Must make/find models that must be Creative Commons 0 (Public Domain), or Attribution (Name of sound and author recorded). | Brandon R | Thursday 14
| Images | Rendering Images to a Quad, and allowing the user to manipulate it (move it around, translation and rotation). | Juriel G | Friday 15
| VR Controls | Allowing the VR hardware to move the camera and controllers to interact with objects and UI.
| Volumetric Lights | Volumetric Lighting to set the tone of the story/video. | Ryan | Tuesday 12 | Conditions
| VFX Graph | Water, Plants, Fire, Pollution. Using Models, images to make effects.
| Post Processing | Edit the post processing.
| Shaders | Make Some Cool Shaders. Raymarching, Water Shaders, etc.
| Timeline | The timeline is responsible for triggering subtitles, sounds, images, videos, and can communicate with the UI controllers.